## Summary Page
Facilities Energy Management Program
Kbtu/sqft Goals |  | 2014 Actual |  |  | 2015 Goal |  |  |  |  | Calculations | [8 empty] | Spring Valley Campus Gas
Building (Campus) | Bldg Sq-Ft | Kbtu/sq ft | lb's of CO2 | 2014 cost | Kbtu/sqft | lb's of CO2 | 2015 cost | Comment |  | kbtu A | CO 2 | kbtu G | [6 empty] | jan | 822204
Centeral Services | 46588 | 56 | 1053889 | 76 | 50 | 948500.1 | 70.68 |  |  | 4.0569 | 105388.9 | 3.6223 | [6 empty] | feb | 645548
Edwards | 64297 | 68 | 1289167 | 101.8 | 60 | 1160250.3 | 94.674 |  |  | 6.7988 | 128916.7 | 5.999 | [6 empty] | mar | 611239
Bristol Hall (Steamboat) | 43503 | 64 | 612332 | 47.6 | 55 | 551098.8 | 44.268 |  |  | 4.3295 | 61233.2 | 3.7206 | [6 empty] | apr | 470352
Hill Hall (Steamboat) | 50000 | 76 | 780721 | 60.4 | 65 | 702648.9 | 56.172 |  |  | 5.9091 | 78072.1 | 5.0538 | [6 empty] | may | 223213
Academic Center (Steamboat) | 68902 | 75 | 1614003 | 130.2 | 65 | 1452602.7 | 121.086 |  |  | 8.0358 | 161400.3 | 6.9643 | [6 empty] | jun | 133663
Spring Valley Main Campus Gas | 155256 | 34.3131 | 582068 | 50 | 30 | 523861.2 | 45 |  |  | 2.2548 | 58206.8 | 1.9438 | [6 empty] | jul | 124623
Sopris Hall (Spring Valley) | 50000 | 29 | 543668 | 36 | 25 | 485461.2 | 33.48 |  | doesn't include gas | 4.4878 | 54366.8 | 4.0275 | [6 empty] | aug | 134930
Calaway (Spring Valley) | 37000 | 78 | 1106449 | 81 | 70 | 1052082.2 | 75.33 |  | doesn't include gas | 3.139 | 110644.9 | 2.8302 | [6 empty] | sept | 221160
Student Center (Spring Valley) | 33092 | 61 | 745721 | 49.4 | 55 | 635076.1 | 45.942 |  | doesn't include gas | 2.8959 | 74572.1 | 2.6053 | [6 empty] | oct | 389979
Coronodo Café (Leadville) | 6675 | 279 | 365055 | 30 | 251 | 290482.9 | 27.9 |  |  | 3.6779 | 36505.5 | 3.2749 | [6 empty] | nov | 800058
Pinnacle Resource (Leadville) | 10800 | 219 | 359510 | 24 | 195 | 323004.5 | 22.32 |  |  | 2.5658 | 35951 | 2.2159 | [6 empty] | dec | 750343
Climax Learning Cent. (Leadville) | 15000 | 110 | 262122 | 18 | 95 | 226171 | 16.74 |  |  | 5.2062 | 26212.2 | 4.6184 | [6 empty] | TOTAL | 5327312
New Discovery (Leadville) | 27000 | 124 | 374373 | 40 | 110 | 348160.8 | 37.2 |  |  | 4.3789 | 37437.3 | 3.9808
Mountain View (Leadville) | 32000 | 88 | 490901 | 32 | 80 | 453463.7 | 29.76 |  |  | 6.8595 | 49090.1 | 6.0021
Breckenridge (Summit) | 36760 | 120 | 790849 | 64.1 | 105 | 741758.9 | 59.613 |  |  | 2.5552 | 79084.9 | 2.2112 | Year | Electric | Heat | Solar | Cost | CO2
Dillon (Summit) | 15800 | 104 | 283661 | 21.5 | 90 | 204576.1 | 19.995 |  |  | 2.713 | 28366.1 | 2.4361 | 2012 | 23118145 | 34840627 | 1210625 | 870147 | 12639898
Glenwood Center | 35605 | 49 | 459285 | 35.5 | 44 | 430918.9 | 33.015 |  |  | 3.3868 | 45928.5 | 3.0789 | 2013 | 27632849 | 35723781 | 1070057 | 1023556 | 14457032
Aspen | 33000 | 66 | 451250 | 35.2 | 60 | 405321.5 | 32.736 |  |  | 5.4715 | 45125 | 4.998 | 2014 | 26545779 | 34310248 | 1010711 | 1083571 | 13887398
Rifle | 33833 | 104 | 470895 | 54 | 95 | 425770 | 50.22 |  |  | 1.4009 | 47089.5 | 1.2316
Carbondale | 9900 | 91 | 191714 | 19.8 | 80 | 144624.5 | 18.414
Total sqft: | 649755
Weighted Average kbtu/sqft |  | 80.1233 |  |  | 70.8148
Total CO2 Emissions (lbs) |  |  | 13776000 |  |  | 12398400
College-wide Cost per Year |  |  |  | 1006.5 |  |  | 934.545
Kbtu goal for 2015 fiscal year is 10%; 2015 cost goal is 7%.
last modified: 4/24/2015 |  | Results displayed on CLEER's Energy Navigator are 90 days behind the current day.
Transportation Carbon Emissions | 2015
Form of Transporation | Gross | Per Person
Vehicular | * | *
Air | * | *
* Vehicular numbers to come from Expense Report data and motor pool.
Total Carbon Emissions
Type of Emission | 2014 Year | 2015 Year
Total Building CO2 | 13776000 | 12398400
Total Transporation CO2 | ?? | ??
GRAND TOTAL CO2 EMISSIONS | 0 | 0
Total Renewables
Campus | Heat Pump | Photo Voltaic
Steamboat (Academic Bldg) | √ | -
Spring Valley (Sporis/Quigley) | √ | -
Rifle | - | 100KW
Leadville | - | 100KW
Aspen | - | 7.5KW
Breck | - | 10KW
Total Renewable usage: |  | 18% *
* this number came from Ennovate who performed CMC's ESCO

## Scorecard
Energy Scorecard | [17 empty] | updated June 11, 2015
Standard Projects | Rifle | CS. | GWC. | Carb. | Aspen | Edw | Dillon | Breck | Calaway | Quigley | Std Cent. | Sopris | New Dis | Mtn View | Library | Climax | Academ* | Hill Hall | Bristol | TOTAL*
System Improvements
Building HVAC Scheduling | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 100%
Classroom HVAC Scheduling | x | n/a | x | x | x | x | x | x | 2015 | x | x | n/a | x | n/a | x | x | x | n/a | x | 73.68%
Occupied Temp Band (4 degrees) | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 100%
Unoccupied Temp Band (55F-85F) | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 100%
Modify BAS system to control Lights | x | x |  |  |  | x | x | x | 2017 | 2017 | 2017 | 2016 | 2016 | 2017 | 2017 | N/A | 2016 | 2016 | x | 31.58%
HVAC Zone Maps | [6 empty] | x | x | [11 empty] | 10.53%
Identify Vampire Loads | x |  |  |  | Aug'15 | [13 empty] | x | 10.53%
Educate staff/students on Energy Mgmt | x |  |  | x | x | x | x | x | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | x | x | x | 47.37%
Building Improvements
Add/Replace Lights w/ LEDs
Parking Lot/Exterior Lights | x | x | 2015 | 2015 | 2015 | x | x | ip | 2015 | x | x | x | 2015 | 2015 | 2015 | 2015 | 2015 | x | 2015 | 42.11%
Large Rooms (Gyms, MPR, Ect.) | 2016-17 | 2015 |  |  | x |  |  |  | 2017 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | x | 2016 | 2015 | 2015 | 10.53%
Small Rooms (Classrooms/Hallways) | 2016 |  |  |  |  | ip | June'15 | ip | 2017 | 2017 | 2017 | 2016 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017+ | 2017 | 0%
Emergancy Lighting | x | 2015 |  |  |  | x | ip | x | 2016 | 2016 | 2016 | 2016 | 2015 |  |  |  | x | x | x | 31.58%
Low FlowWater Fixtures (1.3 gal?) | x |  | n/a | n/a | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 84.21%
Occupancy Sensors | x | 2015 | x | x | x | x | x | x | x | x | x | x |  |  |  | x | x | x | x | 78.95%
Standard Space heaters (Cozy-Legs) | x | 2015 | 2016 | x | x | x | x | x | x | x | x | N/A | x | n/a | n/a | n/a | x | x | x | 68.42%
Building Envelope Analysis | [16 empty] | x | 2016 | 2016 | 5.263%
HVAC Semiannual PM | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 100%
Vending Misers | x |  | x | x |  | x |  | x | 2015 |  |  | 2015 |  |  | n/a | n/a | 2015 | x | x | 36.84%
TOTAL per Facility | 77.78% | 35.29% | 41.18% | 52.94% | 55.56% | 72.22% | 66.67% | 72.22% | 38.89% | 50% | 50% | 43.75% | 38.89% | 31.25% | 37.5% | 53.33% | 61.11% | 64.71% | 72.22% | 52.62%
modified: 4/24/2015 | [15 empty] | LEGEND:
x => Completed ; ip => in progress

## Payback template (Layout) (hidden)
This will be calculation spreadsheet for Return on Investment…………Boyd/Brent/CLEER
Project Description
cost of project
location
projected savings
energy savings: calculated, btu (Help from CLEER)
maintenance savings
capital avoidance
one-time saving: rebates
ongoing savings
other
Payback = number of months
annual btu savings per year

## Payback Template
Payback Calculator
Name of Project:
Expected Completion:
Cost of Project: | 60000 | Total dollar cost of Project
Maintenance Savings/mo: | 750 | Maintenance savings (labor and mat'ls)
Capital Avoidance: |  | Preventave maintenance costs????
One Time Savings (Rebate):
Ongoing Savings:
Other: |  | Other savings. Please specify in comments
Total: | 750
Energy Savings Percentage |  | Energy savings precetage given by vendor.
Projected Savings: | 750 | Total dollar amount of savings per project
Payback: | 80 | Number of months for project payback
Kbtu Savings: | 0 | Anticipated Kbtu savings
Revision: 1.0
Last Edited: 1/30/15
Input Values
Output Values

## Central Services
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Centeral Services | Dec'14 Actual:56 kbtu/sq ft |  |  |  | Dec'15(Goal): 50 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu saving | Comments (where calculated from)
1 | New Windows | PW | 2015 |  |  |  |  | start this fall
2 | New Side roof w/ rigid insulation | PW | 2015 |  |  |  |  | awaiting Udall Grant approval
3 | New RTU's on north building | PW | X | Sept'14 | 66681 |  |  | Done by ATS
4 | Consolidate Friges | PW | x
5 | Standard Heater (Cozy Legs) | PW | 2015
6 | Light Optimization w/ LEDs | PW | June'2015 |  |  |  |  | parts on hand, electrician setup
7 | Add buffer tank to Chiller | PW | x
8 | Tighter Work Schedules | PW | x
9 | Vampire Loads | PM/PW | x
0 | Christmas Shutdown | PM/PW | x | Dec'14
10 | Occupancy Sensors | PW | June'2015
Energy Impact Projects
11 | Visually Inspect Economizers | PW | x
12 | Consolidate M/W, coffee pots, etc | PW | x
13 | Building Envelope Test | PW | x
14 | Water Filling Station | PW |  | May'15 |  |  |  | did 3
Total

## Steamboat
| Facilities Energy Management Projects | [6 empty] | Updated: June 11, 2015
| Bristol Hall | Dec'14 Actual: 64 kbtu/sq ft |  |  | Dec'15 (Goal): 55kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Vending Misers installation | RB | x | x | 336.48 | 300/yr |  | Reduce Energy 35 - 45%
2 | Switch registers to flat plates | RB |  |  | 6500 |  |  | 129 - Replacements @$50.00
3 | Flushing of boilers/glycol loops | RB | [5 empty] | 2015
4 | inspection of insulation levels | RB
5 | Door seal replacements | RB | x | x | 985.5 |  |  | Complete
6 | ensure deadband is 55f overall | RB
7 | visual inspection of economizer | RB | x | x |  |  |  | Complete with rebuilt
8 | vampire hunt | RB | x | x | 0 |  |  | Complete
9 | Improved room by room scheduling | RB | x | x | 0 |  |  | Complete
10 | Outside parking lot LEDs | RB |  |  | ? |  |  | 2015
11 | Retrofit T8's to LEDs | RB |  |  | 16100 | $4802 /yr - 29% |  | 2015/2016 700 - Bulbs @ $23.00
Energy Impact Projects
12 | Air leak test for building envelope | PM/RB | [5 empty] | Winter - 2015
13 | Destrat fans in stairwells | RB | [5 empty] | 2016/2017
14 | LED retrofit on hallway/stairwells | RB | [5 empty] | 2015/2016
15 | High efficiency condensing boilers | RB
16 | Configure windows for a proper seal | RB | [5 empty] | 2015 - July/Aug.
17 | High efficiency condensing DHW tank | RB | [5 empty] | 2015/2016
Total
| Hill Hall | Dec'14 Actual: 76 kbtu/sq ft |  |  | Dec'15 (Goal): 65 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Saving | Comments
1 | Vampire Hunt | PM/RB
2 | Insulate heating pipes in mech room | RB | x | x |  |  |  | Complete
3 | Domestic hot water recirc pump | RB | x | x |  |  |  | Complete
4 | Occupancy controls for the rec room | RB | [5 empty] | 2015/2016
5 | Cozy Legs | RB | x | x | 52 | 427.68/yr |  | Comfort
6 | Reduce ADA door open time | RB | [5 empty] | 2015 July - Sean
7 | Vending miser installation | RB | x | x | 564.95 | 450/yr |  | Reduce Energy 35 - 45%
8 | Consider charging $$ hot laundry | RB | [5 empty] | Stdent Service
9 | Shutdown mini fridges during breaks | RB | [5 empty] | On Going
10 | Visual inspection of economizer | RB
11 | Check outdoor reset on boilers | RB | [5 empty] | On going thru out the year
12 | Use BAS to control parkinglot lights | RB | x | x |  |  |  | Complete
13 | Add BAS control to air lock wall heater | RB | [5 empty] | 2016
14 | Periodic Flushing boiler/glycol loops | RB | x | x |  |  |  | Complete
15 | Replace stepdown registers with flats | RB | [5 empty] | N/A
16 | Condensing boiler replacement | RB
17 | Insulate domestic hot water tanks | RB | [5 empty] | 2015/2016
Energy Impact Projects
18 | Retrofit 'smart lighting' to hallways | RB
19 | Add economizer operation to chiller | RB
20 | Configure 2/3 floors to alerton controls | RB
21 | Upgrade Parkinglot lights to LEDs | RB |  | x | x |  |  | Complete
22 | low flow fixtures for showers/toilets | RB
23 | Air leak testing on building envelope | PM/RB | [5 empty] | Winter 2015
24 | Energy star mini fridge replacements | RB
25 | Upgrade attic insulation to R49 | RB
26 | Window seal replacements | RB
Total
| Academic Center | Dec'14 Actual: 75 kbtu/sq ft |  |  | Dec'15(Goal): 65 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Saving | Comments
1 | Vampire Hunt | PM/RB
2 | Exhaust fan problem in kitchen | RB |  | x | x |  |  | Complete
3 | Try wider temperature deadband to 55f | RB
4 | Visual inspection of insulation levels | RB | x | x | x |  |  | Complete
5 | upgrade registers to flat plates | RB | x | x | x |  |  | N/A
6 | modify lighting to floor by floor operation | RB | x | x | x |  |  | Complete
7 | Wire in daylight sensors for dining hall | RB | x | x | x |  |  | Installed already
8 | Flushing of boilers and glycol loops | RB
9 | Visual inspection of economizer/damper | RB | x | x | x |  |  | Complete
Energy Impact Projects
10 | Upgrade/replace Window Seals | RB | [5 empty] | N/A
11 | Replacement of exterior lighting w/ LED | RB |  |  | ? |  |  | 2015/2016
12 | Replace metal halide track lights w/ LED | RB | [5 empty] | Not cost effected
13 | Check building envelope testing air leak | PM/RB | [5 empty] | Complete
Total

## Edwards
Facilities Energy Management Projects
updated June 11, 2015
| Edwards | Dec'14 Actual: 68 kbtu/sq ft |  |  |  | Dec'15(Goal): 60 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu saving | Comments
1 | Standard Portable Heaters (Cozy Legs) | RR |  | x
2 | Entry Redesign | RR |  | Aug'13
3 | Room Scheduling Changes | RR |  | Oct'14 |  |  |  | New side already scheduled; just did old side
4 | Vending misers/Coffee timer | RR |  | x |  |  |  | 4 machines
5 | Proceed with DHW upgrade | RR |  | x |  |  |  | potentially adding point of use heaters
6 | Replace non-condensing boilers | PM/RR | ???
7 | Parking Lot LEDs | RR |  | x
8 | Building LED's Emergency Lights | RR |  | x
9 | Building LED's fluorescent tubes | RR | 15/16 | partial | $30K
10 | Building LED's office downstairs | RR |  | Nov'14
11 | Building LED cans | RR | 16/17
12 | Energy Impact Projects
14 | Retrofit 'smart lighting' in hallways | RR | x | in proc |  |  |  | harvesting
| Check building envelope | PM/RR
16 | Change/Check Daylight Sensors | RR | [5 empty] | outside (sensor/timer); inside student center dims
17 | Add t-stat button in garage bay | RR |  | done
18 | flushing of boiler/glycol/HX | RR/AS |  | July'14 | 9950 |  |  | Significant improvement
19 | Visual inspection of economizer | RR |  | done
20 | Vampire Hunt | PM/RR
21 | Total
22

## Spring Valley
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Sopris Hall | Dec'14 Actual: 29 kbtu/sq ft |  |  | Dec'15(Goal): 25 kbtu/sq ft (ERROR)
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Vampire Hunt | PM/JC | x
2 | Occupacy controls for rec room | JC | x
3 | Reduce ADA door open time | JC | x
4 | Vending miser installation | JC | x
5 | Mini fridge shut down during breaks | JC |  | x |  |  |  | holiday breaks
6 | Visual inspection of insulation | JC | x
7 | replaced exit signs with LED |  |  | x
8 | occupancy sensors in laundry room |  |  | x
9 | Use BAS to control parkinglot lights | JC | x
10 | Add Bas control to vestibule wall heater | JC | x
11 | Upgrade/replace window seals | JC | x |  |  |  |  | currently caulk
Energy Impact Projects
12 | Retrofit 'smart lighting' for hallways | JC | x
13 | Upgrade parking lot lights to LEDs | JC | x | x |  |  |  | on going
14 | Low flow fixtures to toliets/showers | JC | x | x |  |  |  | transitioning over
15 | Energy star mini fridge replacements | JC | ???
16 | Building envelope leakage test | PM/JC | x
Total
| Calaway | Dec'14 Actual: 78 kbtu/sq ft |  |  | Dec'15(Goal): 70 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Vampire Hunt | PM/JC | x
2 | Visual inspection of insulation levels | JC
3 | Replace registers to flat plates | JC | x
4 | Vending machine miser installation | JC | x | ??
5 | Reduce number of refrigerators | JC | x | x
6 | Resolve gas metering issue | PM/JC | x
7 | BAS programming | PM
8 | Schedule room by room building warm-up | PM/JC | x |  |  |  |  | BAS control
9 | Install daylight controls for atrium lighting | JC | x
10 | Replace parking lot lights to LEDs | JC | x | x
11 | Replace RTU w/ high efficiency units | PM/JC | ??
Energy Impact Projects
12 | Consider retrofit of VAV's on 1st floor | PM/JC | ?? |  |  |  |  | electric re-heat; would need boiler or ???
13 | Cellular/window film to reduce heat loss | JC | x
14 | Building envelope air leakage test | PM/JC | x
15 | Replace eletric to heat pump h20 heaters | PM/JC | ??
Total
| Student Center | Dec'14 Actual: 61 kbtu/sq ft |  |  | Dec'15(Goal): 55 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Replace registers to flat plate | PM/JC | x
2 | Replace RTU to high efficiency units. | PM/JC | ?? |  |  |  |  | insulation
3 | Replace lites in gym to LEDs w/ Occ. sen. | JC | x
5 | install supplemental heating for kitchen | PM/JC | x
Energy Impact Projects
6 | Add button for gym confort control | JC | ??
7 | Add dimming controls to dining fixtures |  | dna
8 | Vampire Load | PM/JC
9 | building envelop study | PM/JC
10 | Upgrade walk in condenser fan blades | JC | 4198800% | x
11 | Replace kitchen appliances to energy star | JC | ??
12 | Total

## Leadville
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Climax Learning Center | Dec'14 Actual: 110 kbtu/sq ft |  |  | Dec'15(Goal): 95 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Scheduling building more aggressively | DT |  | Jun'15
2 | Visual inspection of economizer/damper | DT | 2015-12-14 | 2015-12-14 | 0
3 | change control on snowmelt | PM/DT
4 | vampire hunt | PM/DT
5 | Lower boiler water temp | PM/DT
1 | Retrofit occpancy sensors for gym lights | DT
2 | Replace heating coils w/ 140F coils | DT
3 | Destrat fans for gym & garage | DT
4 | Check building envelope for air leakage | PM/DT
5 | Replace registers w/ flat plate | DT | [5 empty] | comfort
Energy Impact Projects
1 | Retrofit 'smart lighting' to hallway lights | DT
Total
| New Discovery Academic | Dec'14 Actual: 124 kbtu/sq ft |  |  | Dec'15(Goal): 110 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Set temp deadband to 55f | DT |  | DONE
2 | Vampire Hunt | DT |  |  | 0
3 | Visually inspect economzier/damper | DT | 2015-12-14 | 2015-12-14
4 | Daylight sensors on fixtures near windows | DT
6 | Use BAS cntrol on outdoor lighting | DT
7 | Flushing of boiler/glycol loops/HE | DT | 2015
8 | Replace exterior/parking lot lights w/ LEDs | DT | 2015-?
10 | Cozy Legs | DT | 2015-02-15 | DONE
11 | Building envelope air leakage test | DT
12 | Replace registers w/ flat plates | DT | 2015-07-15
13 | Retrofit 'smart lighting' into hallway lights | DT
14 | Energy Impact Projects
Total
| Coronado Café | Dec'14 Actual: 277 kbtu/sq ft |  |  | Dec'15(Goal): 245 kbtu/sq ft
No | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Reschedule HVAC. Separate dining/class | DT | 2015-02-01 | June'15
2 | Limit demand charges (Snowmaking) | DT |  | DONE |  |  |  | Verus Meter installed
3 | Visually inspect economizer/damper | DT | 2015-12-14 | 2015-12-14 | 0
4 | Add timer to fireplace | DT |  | DONE |  |  |  | Turned Off
6 | Operable window blinds. Use at night | DT
7 | Blower door test. Insulation/sealing Upg. | DT
8 | New Windows | DT | 2015
9 | Energy Impact Projects
| Building envelople air leakage test | PM/DT
10 | Replace registers w/ flat plate | DT | 2015-07-15
11 | Retrofit 'smart lighting' | DT
12 | vampire hunt | DT
13 | Total
| Pinnacle Resource Center | Dec'14 Actual: 219 kbtu/sq ft |  |  | Dec'15(Goal): 195 kbtu/sq ft
| Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
No. | schedule hvac | DT | 2015-12-14 | 2015-12-14
1 | Visually inspect economizer/damper | DT | 2015-12-14 | 2015-12-14
2 | Add timer to fireplace | DT
3 | vampire hunt | DT/PM
4 | Blower door test. Insulation/sealing Upg. | DT
5 | Building envelople air leakage test | DT
6 | Replace registers w/ flat plate | DT | 2015-07-15
7 | Retrofit 'smart lighting' | DT
8 | Energy Impact Projects
| vampire hunt | DT
9 | Visually inspect economizer/damper | DT
10 | Total
| Mountain View Res Hall | Dec'14 Actual: 89 kbtu/sq ft |  |  | Dec'15(Goal): 80 kbtu/sq ft
| Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
No. | schedule hvac | DT | 2015-12-14 | 2015-12-14
4 | Blower door test. Insulation/sealing Upg. | DT
5 | Building envelople air leakage test | DT
6 | Replace registers w/ flat plate | DT | 2015-07-15
7 | Retrofit 'smart lighting' | DT
8 | Energy Impact Projects
| vampire hunt | DT
9 | Visually inspect economizer/damper | DT |  | DONE
10 | Total

## Summit
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Breckenridge | Dec'14 Actual: 120 kbtu/sq ft |  |  | Dec'15(Goal): 105 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Ensure setbacks are configured/uniform | BT |  | 2014
2 | Resolve 125KW powerspike problem | BT | 2015
3 | Visual inspection of insulation levels | BT | N/A
4 | visiual inspection of economizer/damper | BT |  | 2014
5 | remote actuation for snowmelt controls | BT | N/A
6 | ensure snowmelt system is off, not idling | BT |  | 2014
7 | re-duct auditorium return air | BT/PM | [5 empty] | make sense?
1 | Barometric pressure logic for snowmelt | BT/PM | fall'2015
2 | Interlock kitchen hood to make up air | BT | N/A
3 | Flushing of boiler/glycol loops/HX | BT |  | 2015
4 | make control point for h20 recirc pump | BT |  | 2014
5 | Upgrade lights to to LEDs in entry areas | BT |  | 2014
6 | Upgrade parking lot lights to LEDs | BT |  | 2015
7 | Resolve air leakage in community room | BT |  | 2015
8 | Building envelope air leakage test | PM/BT
9 | Upgrade insulation level to r49 in attic | BT | 2016 |  |  |  |  | need audit
10 | Replace registers w/ flat plate | BT | N/A
Energy Impact Projects
1 | Install airlock on NW hallway | BT |  | 2016
2 | Upgrade insulation level to r25 in ext walls | BT | 2016
3 | Modify ADA doors delay to minnimum | BT |  | 2015
Total
| Dillon | Dec'14 Actual: 104 kbtu/sq ft |  |  | Dec'15(Goal): 90 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Visually inspect insulation levels in attic | BT | 2016
2 | Replace registers w/ flat plate | BT | 2016 |  |  |  |  | on hold; faculty?
3 | Inspect elevator pump noise |  |  | 2014
4 | Visual inspection of economizer/damper | BT |  | 2014
1 | ensure exhaust fans are scheduled | BT |  | 2014
2 | flushing of boiler/glycol loops/hx | PM/BT | N/A
3 | Replace atomospheric boilers | BT | N/A
4 | Replace RTU #1&2 w/ high SEER units | BT | N/A
5 | Install RTU 'smart' upg. Of VFD & air sen. | BT |  | 2002
6 | Installation of modular heat pump at DHW | BT | N/A
7 | Replacement of exterioir lights to LEDs | BT |  | 2014
8 | install 'smart lighting' controls/fixtures | BT | 2015 |  |  |  |  | add new clock
9 | Building envelope air leakage test | PM/BT
Energy Impact Projects
1 | Roof replacement w/ rigid insulation | BT | 2015 |  |  |  |  | part of roof replace
2 | Vending misers | BT | 2015
Total

## Glenwood Center
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Glenwood Center | Dec'14 Actual: 49 kbtu/sq ft |  |  | Dec'15(Goal): 44 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Vampire Hunt | AM | x
2 | Vending miser installation | AM |  | done
3 | Low flow showerhead installation | AM | n/a
4 | Chiller replacement | AS/AM |  | Sept'13 | 91045
5 | Inspection of economizer/dampers | AM |  | done
6 | Replace outside parkinglot lights to LEDs | AM | Aug'15
7 | Building envelope air leakage test | AM
Energy Impact Projects
8 | upgrade registers to flat plate | AM | x
9 | Electric h20 heaters w/ heat pump units | AM | x
10 | Retrofit T8 fixtures to LED fixtures | AM
| Total | [5 empty] | 0

## Aspen
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Aspen | Dec'14 Actual: 66 kbtu/sq ft |  |  | Dec'15(Goal): 60 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
Calculable Savings
1 | Change to room by room bldg scheduling | PM/AO | Feb'15 | DONE | 0
2 | Visual inspection of ecnomizer | AO | Feb'15 | DONE | 0
3 | Determine source of 15kW spike | AO | x | DONE | 0 |  |  | Kilns
4 | vampire hunt | PM/AO | x |  | 0
5 | Visual inspection of ecnomizer | PM/AO | x |  | 0
6 | Fix radiant loops to prevent overheat | AO | x
Estimated Savings
7 | LED lighting in bathrooms and Art room | AO | Oct'15 | DONE | $15K
8 | LED lighting outdoors & parking lots | PM/AO | Aug' 15
9 | Air leakage test on buliding envelope | AO | ???
10 | Replace step down registers w/ flat plate | AO | X
Energy Impact Projects
11 | Retrofit 'smart lighting' dimming to hallway | AO | 2017
12 | Retrofit T8 fixtures to LED fixtures | AO | 2017
| Total | [5 empty] | 0

## Rifle
| Facilities Energy Management Projects | [7 empty] | updated June 11, 2015
| Rifle | Dec'14 Actual: 104 kbtu/sq ft |  |  | Dec'15(Goal): 95 kbtu/sq ft
No. | Project | Owner | kbtu Saving | ECD | ACD | Project Cost | Exp'ed Payback | Ann'l Actual Savings | Comments
1 | Inspection of insulation levels in attic | JG |  | future |  |  |  |  | TBD
2 | Replace registers to flat plate style | JG |  | x | DONE |  |  |  | 10%
3 | Flushing of boilers/glycol loops/HE | PM/JG |  | x |  |  |  |  | CHILLER IS THE BIGGER DEAL
4 | Vending misers/time clocks | JG |  | Feb'15 | DONE | 245 |  |  | 2) vend (free), 1) snack and 2 TC and misc
5 | rebate plan |  |  | x
6 | Rifle Xmas shutdown 12-23_01-04-15 | JG |  | X |  | 0 | TBD | TBD | Vend miser installed, all 3 micro's unplugged, snack unit off, cooffee pots and coffee vend off
7 | LED parking lot/sidewalk lights | JG |  | X | x
8 | LED building security lights |  |  | Jan'15 | DONE | 1722.5 |  |  | Material = $877.50 and Labor = $845.0013) 100W MH fixtures with Globaltech 30W unit, GTSOLM21-GR-SOLY-120-277-TYPEII
9 | occupancy sensors for HVAC system | PM/JG |  | X | DONE |  |  |  | Still in the BETA test stage-1)unit in Ceramics
10 | Visual inspection of economizer | JG |  |  | x |  |  |  | done by AMS
11 | Misc exterior security lites on out buildings w/ LED & soloar power LED | JG |  | x | x |  |  |  | 70%
12 | Installation of daylight/vacancy sensors | JG |  | Jan'15 | x |  |  |  | 85%
13 | Air leakage test on building envelope | PM/JG |  | ?? |  |  |  |  | TBD
Energy Impact Projects
14 | Integrated Energy Program Start-up | [7 empty] | will use more energy - negative impact
15 | Insluate window shades | JG |  | 16/17 |  |  |  |  | determining plan
16 | Retrofit T8 fixtures to LED fixtures | JG | [6 empty] | PricedLED direct reps/$35 each - BETA testing-Will not work in Bodine B-100 emg ballast
| Total | [6 empty] | 0

## Carbondale
| Facilities Energy Management Projects | [6 empty] | updated June 11, 2015
| Lappala | Dec'14 Actual: 91 kbtu/sq ft |  |  | Dec'15(Goal): 80 kbtu/sq ft
No. | Project | Owner | ECD | ACD | Project Cost | Exp'ed Payback | kbtu Savings | Comments
1 | Vampire Hunt | PM/AM | x
2 | Inspection of insulation levels in attic | AM | x |  |  |  |  | get an audit
3 | Replace registers to flat plate style | AM | x
4 | Flushing of boilers/glycol loops/HE | AM | x |  |  |  |  | review audit
5 | Schedule room by room startup | AM |  | done
6 | inspection of economizer/damper | AM |  | done
7 | LED parkinglot light upgrades | AM | 16/17
8 | 80% efficient boiler replacement | AM | Aug'15
Energy Impact Projects
9 | Retrofit T8 fixtures to LED fixtures | AM | x
10 | addition of economizer to chiller | AM | x |  |  |  |  | control chiller better
11 | Building envelope air leakage test | PM/AM | x
| Total | [5 empty] | 0